## CMS
CMS Tasks :

#	Component	Work description	Priority
1	jsleep scripts	Configuration and finalizing all the init (default), reset, restore and shutdown scripts to all subsystems.
2	jsleep scripts	Batch-file preparation for various observing modes and testing for real-time observing examples.
3	CMS Application browser	Multiple users (at least 15) and long term performance checking.
4	CMS + Wrapper + Device	Bug verifications of near-final CMS.
5	xml, xls files	Tune receiver status monitoring. Configuration settings i.e. default templates for various observing modes.
6	Wrapper	Response certainty for sub-systems' monitoring or for any periodic command i.e. command failed or success. Declared failed only after consequent number of failures and close the session with event=12. Otherwise keep on updating the cms with event=99 and code=10.
7	Timeouts and other parameters tuning	Checking intervals for time-out, dash-board status (CMS state machine) update, login session etc.
8	Wrapper	Device timeout indication using alarm level of 5 by Wrapper.
9	Wrapper	Priority Command at the head of queue
10	Jsleep , drl	Alarm/exception handling. Strictly defining Alarm levels. (Not all alarms are critical). And state machine configuration.
11	Source Coordination + 2d/Polar Plot – CMS Browser	Rechecking of antenna coordinates, object precession, conversion to horizontal coordinate system, rise set etc. correct or not.
12	Wrapper	Deciding about Wrapper machine. Unification of wrapper i.e. All wrappers although common but running on different machines in different directories. All wrapper can be run as a daemon in continuous run mode (if killed restart automatically). Wrappers : (1) servossl_invokeWrapper on 192.168.60.2 (cms application server) (2) backend Wrapper+deviceclient, dataserver wrapper + deviceclient on 192.168.60.31. (3) frontend Wrapper + device client on 192.168.60.4 (4) sentinel and sigcon DeviceClients on 192.168.60.4 machine.
13	Network configuration	(1) Whether all CMS, DBS, wrapper and data machine should be access via only gateway or visible to local LAN. (2) DNS not accepting machine names – connection intermittently break. (3) Future plan about firewall protection and user accessibility

## SUBSYSTEMS
SERVO TASKS :

#	Component	Work description	Priority
1	Initializing script	Putting default safety limits, servotime, antenna offsets, default source parameters, goin/goout in the initializing script.
2	Wrapper -scan	Implementation of scan in RA-DEC/AZ-EL command
3	Event	Displaying of servo Events
4	Alarm handling	Defining and handling alarms event in servo_command.xml and jsleep script.
5	Engineering UI	Setting appropriate units in engineering UI, not all monitoring parameters like motor speed are coming yet. Servo -positioning/track/idle flag indication in color.
6	Global values rechecking	Verifying latitude, longitude, AZ/EL correction ,d-ra,dec,az,el rates and their default values goes appropriately for the calculations

FRONTEND TASKS :

#	Component	Work description	Priority
1	Monitoring	FE + CB Monitoring point yet to be verify
2	FE Command	FE Commands are not working (NGSET, RF ON/OFF, NGCAL)
3	Alarms	Actual critical alarms and exception handling need to be decide and verify
4	FULL BAND	Full Band o/p characterization and verification is needed.
5	FE+CB Characterization report	All RF sub-band need to be characterize at various stages i.e. At the FE+CB o/p at turret, at the LAB and after mixer.

SIGCON TASKS :

#	Component	Work description	Priority
1	Alarm	Necessary Alarm verification and handling
2	Broad spike in first few channels	Mixer o/p probably generates the spike (ref. Shri. Ajitkumar and Navnath)
3	Power optimization	Need to attenuate power level to avoid power saturation at ADC level (ref. Shri. Ajitkumar and Navnath).
4	Characterization and stability.	LO and IF System characterization.

SENTINEL TASKS :

#	Component	Work description	Priority
1	Unit implementation	RFI Shield box or outer box yet to be fabricated and put.
2	Alarm verification	Alarm verification and exception handling like switching power off need to test.
3	Characterization	Temperature unit characterization (raw counts and actual temperature at the shell).

BACKEND TASKS :

#	Component	Work description	Priority
1	machine	Currently using das15m (192.168.60.31), may need one machine for all wrappers+backend/dataserver system.
2	das command	das start/stop repeat gives problem
3	projct,scan info	project,scan info need to be finalize and put into lta header.
4	Tune receiver	Need to finalize back-end parameters
5	gvfits	lta to gvfits conversion
6	python loading application s/w	On new machine – python , Xilink s/w, and required libraries to run backend s/w loading and installation.
7	Backend Status	Backend Status monitoring for e.g. current block, acqusition status etc.

DATASERVER TASKS :

#	Component	Work description	Priority
1	Time domain (chart plot)	Time domain chart plot need to be implemented
2	record	Embeded record (Only one record/data acqusition), UI updating about acq progress.
3	Data Downloading	gvfits or ascii Data downloading
4	pulsar plot	pulsar plot will be implemented after new Roach/GPU based backend.